Agriculture Growth Programme (AGP)

Guideline on Market Centres and Physical Market Development

Draft #1

November,  2009

Table of Contents

Acronyms										iii

- Introduction									1

- The Local context         			                                                            2

2.1.   The General Characteristics of Market Centres in Ethiopia		2

2.2.   Users of Market Centres 							3

2.3.   Prevailing Constraints of Market Centres 				4

3.	The Strategic Approach on How to Develop Market Centres		4

  - Guiding Principles 								4

3.2   Problem Analysis								5

3.3. Criteria for screening and prioritizing market centre

development proposals							6

  - Summary of Criteria to be considered

for AGP investments 						  	 8

- Preparing  Market Centre Upgrading Plan                   			 8

4.1.  Guiding Principles								 8

  - Hardware Interventions (infrastructure upgrading) plan  		 9

  - Software Interventions (Technical support) plan			10

- Developing the Market Centre Management Strategy			11

5.1   Guiding Principles 							            11

  - Defining the Management Structure of a Market Centre		12

5.3   A brief guidance note with respect to the main tasks expected

to be carried by the management body of a market centre  		13

5.4.   Strengthening MMCs and MUs 						14

  - Establishing internal market regulations (by-laws and other

operation procedures) 						            14

  - Suggested areas of training program for AGP intervention 		14

- Monitoring and Evaluation System						15

- Lesson to be Leaned for AGP interventions					16

ANNEXES

- Criteria for Screening and Prioritizing Market Centre

Improvement Project Proposals under AGP			19

B.     Data Collection for a Preliminary Survey of a Market Centre	21

- Case Study: Eric Sprott Market Centre in Bati town,

Oromia Zone of Amhara Regional State				23

D.    List of Further Reading						28

Acronyms

AGP		Agricultural Growth Program

CHF		Canadian Hunger Foundation

FSDS 		Food Supply and Distribution System

IGO 		Inter-Governmental Organization

FAO		Food and Agriculture Organization

MIS 		Market Information System

MMBA	Market Management Bank Account

MMC 		Market Management Committee

MU 		Market Unit

NGO 		Non-Governmental Organization

PCU		Project Coordination Unit

PFS		Partnership for Food Security

RED & FS	Rural Economic Development & Food Security

WDC		Woreda Development Committee

1.   Introduction

The Government of Ethiopia and its development partners are preparing a new Agriculture Growth Programme (AGP) to promote agricultural growth through increased production, productivity and enhanced marketing. AGP aimed primarily at increasing agricultural productivity in a sustainable manner, strengthening marketing and facilitating value addition of selected commodities with due attention to women and youth.

AGP is a five-year program. To achieve maximum impact in the specified period and given limited resources, the program’s target areas are the four big regional states: Amhara, Oromia, Southern Nations, Nationalities and People’s (SNNP) and Tigray.  The primary development objective of the AGP is (please insert text from aide memoire here to complete sentence). Interventions will entail:  (i) comprehensive approaches that include the whole range of production, agro-processing, and marketing of agricultural products through enhancing productivity, value addition, market information and infrastructure in selected target areas; (ii) value chain approach which will embrace producers, assemblers/traders, processors, distributors, retailers and finally consumers to address constraints along the value chain; (iii) high potential agro-ecological zones with a focus in selected high potential woredas; and (iv) decentralized and demand driven (bottom-up) planning, implementation and monitoring approach.

The major components of AGP are broadly categorized into two:  1) promotion of agricultural production and commercialization, and 2) rural infrastructure development to enhance productivity and value addition. The rural infrastructure development component of AGP has two sub-components of which improving market infrastructure is one.

The “Market Infrastructure Development Sub-component” of AGP is meant to enhance efficiency of market performance and includes developing rural roads, upgrading   physical market centres and promoting post harvest handling and agro-processing infrastructures. Besides upgrading or construction of feeder roads, AGP will support construction of modern market infrastructure comprised of community warehouses, public potable water supply and toilets, inclusive of any needed capacity strengthening for community management of public assets for sustainable use. The improved market centres in general play an important role in improving agricultural marketing. They can:  (i) provide a location at which farmers can meet with traders; (ii) increase retail competition by providing a convenient place where farmers can meet with consumers; (iii) improve hygiene by introducing practical changes to sanitary practices; (iv) reduce post-harvest losses by providing protection for produce from direct sunlight, rain, etc.; (v) make marketing a more pleasurable activity; and (vi) provide a focal point for rural activities.

Although the infrastructure that would be needed in the market centres will emerge from the market needs assessment through participative consultation, possible/illustrative infrastructural facilities that would be provided in the market centres include (a) paving the market site (b) constructing market shed (c) toilets (d) community warehouses (e) access roads; and (f) water supply. Soft interventions also include training on market management; improvement of commercial activities; and facilitation financial service provision for market users.

This guideline provides practical advice for upgrading market centres located in rural, peri-urban and urban (zonal and/or district towns) areas within the geographical coverage of AGP. The objective is to initiate an inclusive community sub-project where traders, farmers, women, youth and unemployed play a leading role in the decision-making process and have greater access to upgraded infrastructure and facilities. This document is prepared primarily based on FAO technical publications, Government of Ethiopia guidelines, and experiences in related fields (design and management of markets) and from an extensive literature review.

The primary purpose of this guideline is to assist AGP implementing bodies at federal, regional, woreda, and community levels to judge whether market centre upgrading should be made and to guide them through the bottom-up designing and planning process of the sub-project and its implementation with the participation and ownership of primary beneficiaries (market centre users). Though the guide is aimed at people engaged directly or indirectly in the implementation process of the AGP, it can also serve as useful reference material for people working in any program that embraces market infrastructure development.

2. The Local Context

  - The general characteristics of market centres in Ethiopia

In Ethiopia, market centres are locations where agricultural producers, traders and consumers come together for commercial purposes: supplying, selling and buying goods. Markets also serve social purposes, playing an important role in the social life of rural and urban populations, and by providing formal and informal temporary income-generating activities for the unemployed.

There are different types of markets: those established on a plot of land, in a building, a temporary structure, a semi-permanent structure, mobile stalls or fenced-in areas. In rural Ethiopia retail market places  are usually open air markets and can be included in a project plan as a commercial centre, market area or a piece of land utilized spontaneously.

Rural markets, in terms of physical characteristics, can be classified as ‘central markets’, ‘neighbourhood markets’ and ‘village markets’. The central market is usually located at a critical point in the overall transportation grid: typically all the surrounding market area becomes a ‘commercial centre’ where all variegated trading activities are located. The centralization of all commercial activities in one location has significant effects on congestion in and around the market area. These ‘commercial centres’ are usually where people have a wide array of product choice and can interact socially. The neighborhood and village markets are usually periodic general markets that supply remote areas.

In rural areas, an agricultural market is often a section of the central market where a variety of local or imported products are sold, including fresh and processed crops, meat, dairy products and fish. Most market places are managed by the public sector that mainly collects taxes and define pace and zoning criteria. The official list of approved market traders -if one exists -rarely corresponds to reality; subleasing and the use of figureheads are common practice.

Market cleaning services are provided by the public sector and commonly are inadequate and insufficient. Water services often do not exist or suffer from serious management problems. Sanitary facilities are usually present, but they are overpopulated, expensive or do not work properly and consequently suffer from poor hygiene conditions. In most of the markets, storage facilities and security services are

informally managed by traders.

Usually, according to the master plan, there is an open-air market of three to four hectares without any facilities. In some cases, there are shelters used by the traders of second-hand clothes and several illegal permanent buildings used as housing and storage facilities by wholesalers. The agricultural market is a section of the marketplace and usually the traders have no shelter or at most, they have mobile ones.

Products sold in most market places across the country include the following:

• Grains, Vegetable and root crops (onions, garlic, tomatoes, salad, green pepper, carrots, potatoes, cabbage)

- Spices, salt, coffee, sugar cane, fruit, local oil;

• Livestock (cattle, shoats, horses, donkeys, mule, camel, etc)

- local alcohol;

• eggs and chickens;

• milk, cheese and butter;

• locally produced handicrafts;

• second-hand clothes;

• charcoal;

• various imported tools (made of plastic, wood or glass).

2.2.    Users of Market Centres

Farmers (traders of different agricultural products). They are present in most cases during the main market days and for a limited time. On a market day, they sell their products, buy others, do other business in town, and then leave to go back to their villages. For this reason, they often prefer to sell all of their products to other traders rather than be engaged in time-consuming retail activities.

Wholesalers/mediators. Their activity is somewhat limited and not very significant. This is caused by the lack of infrastructure, namely storage facilities and effective transportation systems. Farmers prefer to go directly to the market because the scale of their activity is too small to justify the loss in income of selling to wholesalers, and farmers can take advantage of their trips into town to do other things.

Retailers. They generally live in the urban area, but some of them come from outside the urban area for the main market days. Usually they perform their activity individually because they are unable to identify common objectives and instruments. The scale of their activity ranges from the sale of only one product, usually butter, milk or vegetables, to much more profitable general trading such as spices, fruits and cereals. In any case, the retailers are definitely the most numerous group in the markets and most of them are women.

2.3.   Prevailing constraints of market centres

Institutional factors. The local municipality is usually responsible for the management of the market area. The revenue office (finance section), in charge of collecting taxes, is the institution that is more involved in the market. The health section should conduct public health inspections, but generally it is involved only with slaughterhouse activities. No real services are guaranteed, and the cleaning service does not work properly. The assignation of stalls is sometimes on a first come first served basis, other times it is a question of habit.

Underdeveloped infrastructure and facilities. In most of the market places, hygiene is completely neglected. Products are displayed on the ground, even the most perishable ones like dairy products or fresh vegetables; there are few mobile structures and they are used by the richest traders (clothing and industrial product traders). More often, cleaning services are not available market places. In addition, the drainage system is inefficient. During the rainy season, mud and water make it very difficult to sell and cause serious risks of food contamination and disease transmission. The lack of storage leads to additional daily product losses because the women must transport all of the perishable commodities by donkey or on their backs. Moreover, there is no water inside the market area. In some markets, public toilets exist but they are expensive and usually they are not used.

- The Strategic Approach on how to Develop Market Centres

  - Guiding principles

The lessons learned from a number of experiences suggest that developing a market centre should take into account the following factors, which should also be given due emphasis during the planning and implementation process of market centres subprojects to be financed by AGP.

i) Communities should take the lead and ownership of the project. Local people

should become market place ‘proprietors’. All stakeholders need to participate in the process to develop a sense of ownership and have the opportunity to increase their knowledge through training and discussion.

ii) A market centre development project should take into account also environmental, social and gender dimensions. If market centres upgrading projects focus narrowly on economic and financial elements, there will be a risk of relegating their social function to a secondary role. The establishment of new services and new taxes entails the risk of increasing both social exclusion inside the marketplace and inequality between rich and poor traders. The main victims are likely to be women traders. The challenge of such intervention is to address the constraints that impede women traders’ access and commercial development. Moreover, due attention should be given to any environmental consequences of the intervention.

iii) The ‘soft’ and ‘hard’ elements of market centre development project need to be complemented and integrated. The ‘soft elements’ include community participation and the mechanisms to facilitate it (involvement in all project phases, training and capacity building); the ‘hard’ interventions are the infrastructure improvements (upgrading buildings and facilities, etc.). Soft and hard elements have to go hand in hand and be complementary. The soft elements have to be included in all phases of the infrastructure upgrading to create a social environment where the stakeholders involved have more capacity, interest and a sense of ownership in order to better manage and sustain infrastructure interventions.

iv) All stakeholders need to be mobilized and actively participate in the development process. In order to develop a participatory decision-making process and follow-up all the project phases, a local work team needs to be set up and can be composed of:

- traders representatives (women/men);

- market association representatives (if there is any);

- local government representatives;

- key informants;

- other resource people (according to the specific context).

  - Problem analysis

Step one: Identify the problems

A critical analysis of the problem is the first and important step to verify the need for investment in upgrading a market centre and to justify such an intervention. For doing so, the first step is to identify main constraints inside the market place.  In most cases, problems of existing market centre include:

- very poor hygiene conditions in the marketplace and inadequate facilities;

- most small-scale traders drive from their market activities a very low daily net income, which is  caused by product losses, seasonal availability of the products, lack of market information, intense competition with informal traders and insufficient initial capital;

- Inadequate market place management; etc

Step two: Determine if marketplace upgrading is a priority

In this case, there is a need to review problems that may be solved by either new or improved market centre, and identify the kind of intervention that will most benefit local communities and potential users of the market centre.

- Is the problem one of the main problems within the Food Supply and Distribution System (FSDS) of a specific rural area?

- Is the problem a major bottleneck along the value chain system?

- Is the intervention the best way to improve household income (particularly for women)?

- Does the intervention stimulate the target woreda’s agriculture production and productivity?

Step three: Identify the main objectives of the market centre upgrading sub-project?

In most cases the objectives can be summarized as:

- strengthening food safety by providing a healthier environment with basic infrastructure and facilities in the marketplaces where hygiene conditions are poor and the risk of food contamination is high. This could also have an impact on the preservation of fresh products and on their nutritional value;

- reducing the losses of perishable agricultural products by providing appropriate shelters, storage and water facilities; and

- improving marketing efforts by providing training in marketing and promoting traders’ associations.

    - Suggested Criteria by AGP in screening and  prioritizing market centre to be upgraded

AGP’s investment decision on market centre development need to be made based on the following criteria.

    - Selection criteria based on an analysis of the infrastructure and economic

context

- The existence of other initiatives related to improving the FSDS (e.g. road construction/upgrading/maintenance, market construction, urban and pri-urban agricultural development in the areas surrounding the market, improving agricultural production, agriculture diversification initiatives, training programmes for merchants or farmers, financial services, etc.);

- The extremely poor hygiene condition of the area (the absence of shelter, drainage system, water, toilet facilities, etc.);

- High volume of perishable products and high losses caused by a lack of market facilities;

- Significant amount of daily gross turnover for agricultural products;

- The expected impact of upgrading the market centre in terms of improving the marketing system as a whole and  improving the livelihood of farming communities in the catchments area and exploiting the commercial potential of the area

    - Selection criteria based on an analysis of the stakeholders

- Small-scale traders prioritize the market upgrading subproject among other initiatives;

- The traders are willing to accept higher rents and taxes to cover (at least partially) the operation and management costs of the centre;

- The local government is contributing financially toward upgrading the market centre;

- Traders’ associations (if there are any) want to contribute to market upgrading in terms of financial resources or man/woman power;

- The traders are willing to create organizations, such as cooperatives and micro-enterprises if they do not exist.

Needs assessment of market stakeholders

A list of priority needs of stakeholders has to be identified at the following levels:

• the physical area;

• commercial activities;

• market management;

• vulnerable groups.

Note: for further detail about the selection criteria of market centre project proposals

see Annex A.

3.3.3. 	Additional information to be gathered about the target market centre

i)   Survey of the selected market area

Basic data and information are collected before the project begins which will also be used to assess the progress made and to develop the monitoring and evaluation system.

The main purposes of the survey are:

- to prepare the action plan based on the agreed objectives; and

- to design the baseline assessment.

The steps to be taken to collect data:

- list the necessary data and the possible sources;

- verify the reliability of the available data (e.g. list of traders, maps, average annual sales for the market, taxes collected, etc.);

- create a specific survey team to collect the required information and mobilize available resources. The team could be comprised of:

  - engineer/planner from the municipality;

  - a person responsible for tax collection;

  - a person responsible for sanitation in the area;

  - a gender expert from the women affair office or women association at woredas level;

  - a representative of traders and/or farmers;

  - a representative of the traders’ associations (if exist); and

  - other key people, who are knowledgeable about the marketplace, the traders and market channels;

Areas of data to be compiled

The survey process starts with the collection of data concerning:

- infrastructure assets;

- mapping of the marketplace in terms of its geographic features, master plan area, trader placement and distribution, and physical infrastructure;

- commercial activities;

- market management;

- socio-economic situation of market traders (particularly of women);

- farmers and middlemen inside the market area; and

- small-scale female traders inside the market area.

Note: for further detail about areas of survey data information to be collected as part

of designing a market centre upgrading program see Annex B.

  - Summary of illustrative criteria to be considered for AGP investments

It is suggested that the subproject proposals submitted to upgrade market centre shall be evaluated based on the following criteria.

- Very poor sanitary conditions of the market centre

- Linkages and complementarities with other AGP interventions

- Population served no less than 100,000

- Market area covered by the traders of perishable products in the centre (at least 3000 meter square)

- Agricultural products and locally produced perishable commodities sold in large quantity and the demand for perishable products growing

- Market centre upgrading prioritized by the community or according to district planning guidelines

- Contribution from the municipality (or woreda/zonal administration) in terms of cash contribution (minimum 10%) of the total project cost

Additionally, decision makers (particularly municipality officials) should take into account the following factors when upgrading a market centre through AGP support.

- The availability of adequate space  for sales areas, storage, administration, specialized facilities, circulation and parking

- The potential size of land (space) allocated for a market centre in terms of allowing both for future expansion needs and for adjusting the space utilization of the market to match management requirements to meet changing social and economic circumstances;

- The type of physical infrastructure (building designs) to be developed in terms of allowing maximum flexibility for future change. For instance, for peak periods, and for simple rural and urban retail markets, emphasis should be given to the use of low-cost covering of sales areas, either by using permanent light-weight shade structures or retractable blinds.

4.      Preparing Market Centre Upgrading Plan

  - Guiding Principles

Under AGP, interventions related to market infrastructure development are being considered as community investment subprojects; which means, its planning and implementation process shall adopt the guiding principles, procedures and steps outlined in AGP’s guideline document known as “Community Level Participatory Planning Process Guideline”. Market centres upgrading is one of the community asset building types of investments which are not directly generating incomes for groups or farm households but build community assets which in the long run will benefit the whole community. At planning phase this subproject could be planned by the development committee at regional or woreda level (depending on the size of investment and capacity required) with intensive consultation of market centre users and community members who will be affected directly by the intervention. However, during its implementation stage a separate management committee, which will function under close follow-up of the woreda development committee, is required. Committee members are to be nominated from within common interest group to implement and monitor the centre.

The upgrading subproject plan document should show a list of prioritized ‘hard’ and ‘soft’ interventions.

Hard interventions include:

- land use plan;

- building construction/upgrading;

- facilities construction/ upgrading;

- access and circulation management.

Soft interventions include:

- market management;

- improvement of commercial activities;

- financial services (integrating appropriate financial system);

- training programme; and

- support for social inclusion of women small-scale traders.

4.2.   Hardware interventions (infrastructural upgrading) plan

4.2.1.  Guiding principles

The approach proposed here is a process that can facilitate the development of a sense of ownership, thus the scale of physical infrastructure intervention might usually be  limited. If the intervention is appropriate and tailor-made, and if traders - both women and men - are part of the decision-making process, they will consider themselves as owners and take responsibility for the marketplace. Traders will also continue the upgrading process by mobilizing additional local or external resources.

The total daily gross sales of most rural markets are usually not enough to justify complex physical structures. The users of rural markets are low-income traders, most of them cannot cover the cost of complex construction/upgrading projects and do not have the financial resources to maintain the building(s), thus simple and low-cost infrastructure and facilities shall be promoted through AGP investments.

4.2.2.   Components of the physical infrastructure upgrading plan

a)  Land use plan

A general layout should be prepared for the entire market area showing:

- the intended use of the market area, showing different areas for food, industrial products, meat/fish and agricultural products;

- access, parking and waste disposal areas;

- internal circulation system; and

- the area for farmers, retail and wholesale merchants as well as permanent and temporary traders.

b)  Improving point of sale for agricultural products

Priority consideration should be given to:

- the upgrading/construction of the pavement, with an appropriate drainage system;

- permanent shelters for permanent traders;

- mobile shelters or a simple paved area for temporary traders;

- the area where perishable agricultural products are sold;

- available local materials, if they do not require a lot of maintenance; and

- building point of sale on a different level than that used by pedestrians, to ensure a healthy environment.

c)  Drainage system

The drainage system has to be upgraded in all of the surrounding areas of the market in order to ensure a healthy local environment. An open drainage channel would facilitate cleaning.

d)  Water facilities

This includes drinking water as well as water used for washing products and cleaning the market area. The possibility of using roof-top water harvesting technology should be considered.

e)  Toilets

Toilets are usually provided by the municipalities, but they are often dirty, poorly managed and expensive. A model for providing and operating well-constructed and well-managed toilets could make the market area a demonstration site for sanitary improvement.

f)  Storage facilities for retailers

Overnight storage facilities should be developed, used and managed by sell point owners.

4.3. 	Software interventions (technical support) plan

    - Conducting market studies

The aim of a market study is to help design an appropriate marketing strategy. A marketing strategy is necessary to improve commercial activities that are important in making market centres work. A market study can be conducted to test the performance of products already available in a certain market and/or to introduce new products. A study on the existing and potential demand by product or service should be conducted in order to obtain the basic information necessary to provide a comprehensive understanding of the different opportunities for defining a marketing strategy.

The market study should be based on qualitative data collected from a representative sample of different customers. In most cases, some ‘guess work’ will be necessary in order to assess both present and future demand. The main components of a market study are:

i)  Market size and growth. What needs to be considered are macro-economic and financial variables, for example, inflation and unemployment rate, cost of fuel, government policy, possible salary increases, and demographic growth, etc.

ii)  Consumer behavior. The market for any product can be split into individual segments, where each segment describes customers with similar socio-economic levels, requirements, tastes, characteristics, interests, religious faiths and lifestyles.

- Needs and priorities of the different segments;

- level of satisfaction and quality of existing services;

- specific demand for each product in terms of periodicity, availability and quality;

- service or product desired; and

- price perception, affordability and willingness to pay.

The analysis should consider the present or actual demand during the different periods of the year. A targeted analysis of demand focused on a representative sample of other actors in the market (farmers, middlemen and traders) could also be useful to justify the opportunity to provide a specific service such as the Market Information System (MIS).

    - Establishing or strengthening market traders’ associations

If traders’ associations exist, a detailed analysis should be carried out to understand their role inside the community. Market traders’ associations - or cooperatives - should be promoted through training aimed at making traders aware of the various benefits including the opportunity to reduce their transaction costs. Technical support can also be required to define internal rules, business plans and to manage internal conflicts. Farmers cooperatives involved in marketing activities may also need capacity building support through AGP so that they will play in and benefit from the development process.

- Developing Market Centre Management Strategy

  - Guiding principles

Management of a market centre is one of the most important aspects that can, to a large extent, determine its effectiveness and sustainability. Upgraded market centres that are not used, lack of maintenance and cleaning services are common and are usually caused by inappropriate market management. Market centres are normally managed by local government, which does not have the interest, time and, in some cases, the technical capabilities to provide appropriate management. Even when local governments inject cash into market upgrading, management still remains inefficient. However, experience demonstrates that markets can be appropriately managed when market users are directly involved in the design, implementation and M&E of the project.

The presence of full-time management staff is not viable from Ethiopia’s context. The simplest solution is for market centres management to be run by users themselves, facilitated by the local government. Depending on the context reasonable perdium allowances could be budgeted as an incentive to some of all of management committee members.

  - Defining the Management Structure of  Market Centre

Complex market centre management structure may not work effectively in Ethiopian context in general, and in the context of woredas targeted by AGP in particular, where simple procedures would be more appropriate and most effective. Therefore, the following institutional structures are suggested for AGP intervention.

- The Market Management Committee (MMC): to be established by a minimum number of seven members (traders representatives) elected by traders  themselves.

The responsibilities of MMC are as follows:

- Place assignments (in collaboration with the municipality)

- Encourage the creation of associations among the traders (in cooperation with the woredas cooperative department or trade and industry department)

- Define the internal roles within the market (in collaboration with the traders) and put in place corrective measures

- Open and manage  a bank account to cover fixed costs (maintenance and cleaning) and if there are enough funds, for eventual market services (such as water, sanitation, light or market expansion). The chairperson, secretary and treasurer of the MMC have to be co-signers of the account to be opened.

If some type of organization already exists and is already responsible for some aspect(s) of market centre management, an assessment will have to be made to determine whether to continue with the current structure or to change the management framework.

ii)      The Market Unit (MU): which is made up of one representative from the

local government (Woreda Development Committee(WDC) member), a representative from the municipality,, one from trade association, one from the office of women affair/ women association (if any), one representative from the MMC, and other representatives from important constituencies (depending on the local context).

The responsibilities of MU are as follows:

- Auditing the management of the bank account;

- Making sure that the MMC provides appropriate cleaning and maintenance of the market area;

- Managing the allocation and collection of taxes and rents. In terms of taxes/rent, the municipality will continue to collect the same amount paid before the market centre upgrading effected. After two years, any increase in taxation could be considered which has to be also endorsed by the MU and the MMC.

- Up on delegated by the development committee, the role of the municipality will be: auditing the efficiency, transparency and effectiveness of the MMC. The AGP focal person at woreda level will play facilitation and coordination role in the management process of a market centre.

- Other stakeholders

The staff working in  AGP’s Project Coordination Units (PCUs) and development committees established at regional and zonal levels will play significant role in the designing, planning, and implementation of market centre development subprojects. Their responsibilities include, but not limited to:

- facilitating the establishment of MMCs and MUs and monitoring the performance of the subproject;

- facilitating the provision of different trainings for the MMCs, MUs,  traders, traders associations, farmers’ marketing cooperatives, etc;

- facilitating the provision of technical support in ensuring the integration of gender and environmental factors; and

- reviewing and approving work plans and periodical performance reports

In general, the main responsibilities of the management body of a market centre development program is  to operate a well-functioning organization, which includes defining procedures for ensuring: effective market operations; application of rental and stall-allocation policies; revenue collection and appropriate revisions to rental levels and daily fees; operation of market rules and regulations; dispute resolution procedures; effective traffic control and management; enforcement of environmental, public health and food safety requirements; mechanisms for meeting recurrent and periodic maintenance requirements; and future improvement and expansion of facilities.

5.3.	A brief guidance note with respect to some of the tasks expected to be carried out by the management body of a marketplace

a)  Assigning places

There is no objective method for assigning market stalls or spaces. The assignation could be done by defining some rational criteria (e.g. if the market has been upgraded for agricultural perishable commodities, the users previously involved in that commercial activity should be prioritized). The assignation could be done by lottery or by using some other criteria decided upon by the traders (e.g. age, gender, seniority within the market, etc.). Priority could be given to women petty traders.

The responsibility for carrying out the assignments, in order to avoid social conflicts or a situation where the upgraded market is not utilized and all the traders sell in the surrounding areas, should fall on the traders’ representatives (the MMC and the MU). In some markets where ethnic, gender or social problems exist, the presence of an external stakeholder as facilitator could be necessary to manage social conflicts.

b)  Taxes/rents

Traders have to pay a tax on their commercial activity as well as rent for the use of public land. The amount to be paid could remain the same as it was before the upgrading intervention for the first year. It could be increased for the following years, if the MMC approves the change. The responsibility for collecting tax and rent will fall on local government/municipality. Occasional supervision from an external agency (an NGO or advisor in charge of monitoring the market upgrading process) could be considered.

c)  Infrastructure and facilities management

Traders themselves have to manage and maintain the infrastructure and facilities provided. They have also to provide a daily cleaning service (employing someone or doing it themselves). As this requires funds, a Market Management Bank Account (MMBA) should be opened and managed by the MMC under supervision by the MU.

For a cleaning service, the local government/municipality will be responsible for collecting the garbage from the waste dump on an agreed frequency, no less than once a week, depending on the volume of waste and climatic conditions.

5.4.	Strengthening MMCs and MUs

Usually the stakeholders do not have experience in market centre management. An important component of the strategy could be providing on-the-job training to the MMC and to the MU. In most cases, especially in market areas where the stakeholders do not have previous experience in market management, an external agency (such as a private company or local NGO) or advisor will be necessary to accompany the development of the management process for one to two years.

Financial support may be necessary for the setting up of a market committee. The types of temporary support (for the first one year) that AGP could  provide to a committee may include: partially or fully cover the initial investment costs of office furniture and equipments; minor financial support to cover travel and other expenses of the committee members; and partly finance operation and administrative costs (including office rent) at least for the first six months to one year period of the project.

5.5.    Establishing internal market regulations (by-laws and other operational

procedures)

This is essential for managing the market place and for managing conflicts. Experience demonstrates that when there are rules and all the market users accept them democratically, it is easier to manage conflicts.

The regulations will be prepared by the traders and the MMC in collaboration with some project staff (AGP focal person at zonal or woreda level serving as a facilitator) and external technical support (if necessary). These regulations should be reviewed and endorsed by the MU. The regulations should be translated into a local language and be made visible and available to all the stakeholders. They will address the following issues:

- gender equality;

- place assignment (e.g. timing, products sold);

- penalty to be paid in case of violation of the rules (e.g. sub-leasing, non-payment, failure to clean, etc.) and other marketing practices;

- contribution to the MMBA;

- election of the MMC and MU representatives (how long they can remain in office, the minimal percentage of women and their responsibilities, etc,);

- cleaning services (responsibility of each trader);

- security and fire safety; and

- marketing practices.

5.6.   Suggested areas of training program for AGP intervention

AGP’s proposed training program related to the management of market centre will focus on leadership and communication, bank account management, the infrastructure maintenance of the market centre, gender issues, social conflict management and marketing activities. These trainings will be provided to all the members of the MMC and of the MU  in order to allow them to carry out their role in a better way.

The AGP program can also facilitate the provision of the following specific trainings (for women and men) aimed at different groups with specific tasks. The training is also tailor-made, but usually it deals with the following issues:

- safety and sanitation issues (for the traders) through providing basic information on cleaning, selling and storing, and clear explanations of all the risks associated with an unhealthy environment and contaminated food;

- market association (for the traders) explaining the benefits of creating an association of traders (micro-enterprise or farmers cooperatives) and supporting them to create an organization;

- marketing activity (for the traders) explaining how to improve their commercial efforts, the opportunity to diversify the agricultural products sold, access to market information, the linkages with farmers and middlemen;

- facilities management and maintenance (for the MMC and the MU) explaining how to calculate the tariff plan and how to differentiate the plan according to the different utilization of services;

- Bookkeeping, financial management and bank account management (for the treasurer and the members of the MMC).

Basically, it is expected that most of these trainings would be embedded within and delivered as part of other component and sub-component activities of AGP. Hence, the software intervention elements of market centre development need to take into account this integrated and coordinated approach of project implementation.

- Monitoring and Evaluation System

In principle, it is expected that the monitoring and evaluation system of a market centre development subproject (as part of market infrastructure development) will be treated under the overall monitoring and evaluation system of AGP. But, it may also be appropriate to introduce a separate monitoring system (a subset of the overall M&E system) which would be used specifically to oversight subproject activities through which gaps between what was planned and what is actually occurring are identified and corrective measures proposed.

The main purpose of this separate M&E system is to collect and analyze data and provides information, which MMC and MU can use to identify and solve implementation problems, and assess progress in relation to what was originally planned. The information gathered and analyzed through this sub-system designed  specific to market centre development subproject will be used as an input to the overall M&E system of AGP.

Usually a monitoring system needs:  clear project objectives; essential data for achieving each objective;  and well-defined performance indicators able to measure progress towards the objectives. In this regard, the market upgrading programme usually has the following specific objectives:

- objective 1: improve the hygiene conditions of the market areas;

- objective 2: decrease the losses of agricultural products after market upgrading

interventions;

- objective 3: increase the efficiency of commercial activities;

- objective 4: establish an efficient MMC for the upgraded market;

- objective 5: make the upgraded market more accessible to women petty traders.

The data collection will be based on identified indicators corresponding to the above stated objectives. In the beginning, the person responsible for developing and managing this M&E system will be someone employed by the AGP; later, it can be someone from the MU (municipality staff) supported by AGP for a while. The person responsible must be trained on how to update the database and analyze the monitoring data in order to suggest corrective measures or additional interventions.

Starting from a simple baseline, defined during the initial phase, sensitive data has to be collected to monitor impact using selected indicators corresponding to the above mentioned objectives. Depending on the context, a database programme or a simple data log could be utilized.

- The Lessons to be Learned  for AGP  Intervention

i)    The Enabling Environment

If the enabling environment is not favorable to private sector participation, decentralization, community empowerment and gender approach, the market centre-upgrading programme will remain an isolated intervention and the sustainability of the project will be difficult to achieve. The real interest and involvement of all stakeholders, and government policies and regulations that facilitates the achievement of the proposed objectives, are prerequisites for sustainability.

The presence of traders in the MMC and the participatory approach to defining project strategies can create awareness and stimulate social mobilization, but this does not guarantee that traders will play any part in the market decision-making process, which is usually led by the municipality. This leads to a poor sense of ownership which hinders a genuine incentive for traders to optimize the use of market structures. The participation in the decision-making process is effective only when some facilities (maintenance, toilet, electricity, etc.) are managed by the traders themselves.

It is strongly recommended that significant investments be made in soft interventions. On-the-job training and appropriate monitoring systems for market management, creating market associations and improving marketing activities are all essential issues for empowering traders, including women and ensuring the future sustainability of the market upgrading programme. Petty traders also need access to credit. Moreover, dissemination of information about financial service options inside the market area is strongly recommended.

ii)   Gender and environment

Gender inclusion implies more than making a social assessment of the role of women in the market and their degree of exclusion. Women have to become an integral part of the decision-making process through having access to credit, contributing to marketplace assignments, having access to training, and forming an integral part of the MMC and MU.

Environmental issues need to be taken into account at an early stage to ensure that any positive impact is maximized and any negative impact is either prevented or reduced to a minimum. A well-formulated market centre development should not have a negative effect on the environment or on the local population. Any negative impact can be reduced, but at a cost. It is better, therefore, that the potential impact is recognized from the beginning.

iii)   Managing social conflicts

Ethnic conflict, religious conflict or gender inequality could emerge during a market centre development project. There is the real risk that the market could remain empty or that the actual beneficiaries are completely different from the intended ones. The role of the facilitator, as a social mediator, is essential in a market centre upgrading strategy from assigning places up to the monitoring phase.

iv)   Infrastructure upgrading

The financial resources of rural market traders and of local governments are usually very limited. Generally upgrading is financed by an external agency with a small, but very important, participation from local government or stakeholders. The potential of cost recovery is very small in justifying such a large disbursement of money. Therefore in this context an upgrading project has to be evaluated on the basis of social and local economic indicators, for example, improving sanitary conditions, reducing product losses, facilitating the creation of associations and a sense of ownership. The upgrading has to be flexible in order to be adaptable to market changes and possible future evolutions.

v)   Exploiting the commercial potential of upgraded market centres

The market centre upgrading programme is a development process that should continually exploit all the potentials of an upgraded market. The creation of a traders’ association, the tailor-made on-the-job training and microcredit system, the improvement of the institutional context and an appropriate market management strategy are the necessary conditions for improving marketing activities. On the other hand, all these components have to be considered as a ‘starting point’ for the market centre upgrading process; they are necessary but not sufficient for supporting the potential economic development of the upgraded market areas. Some suggestions for AGP intervention  could be:

a)  Strengthening associations. The  creation of micro-enterprises and cooperatives could be extended to encompass petty traders of agricultural products (such as the traders of cereals, sugarcane, spices, and small farmers that sell directly to customers on the main market day). Those organizations, together with the existing ones, could try to facilitate linkages with farmers, middlemen and wholesalers in order to improve their marketing activities.

An umbrella organization created through a strong network of market users (associations and cooperatives) would help facilitate access to low-cost means of transportation, like a donkey cart, as an important component of the gender-sensitive approach. In most rural areas, women farmers walk several kilometres to and from the market because hiring trucks is too expensive for them. For instance, facilitating the creation of a low-cost transportation cooperative could be crucial for improving the quality of life and reducing losses caused by inadequate transportation.

b)  Partial specialization of the general market area. The assembly market (a small area where farmers, middlemen and traders meet during the market days for a couple of hours) exists in each marketplace. It could be improved by facilitating better linkages between traders and producers to reduce transaction costs and ensure a good price.  The opportunity to develop an assembly centre for some agricultural product markets, which is located in a convenient area, should be looked at because it could serve as a midway point for commercial transactions and storage for these products, facilitating the supply for certain market centres.

c)  Market service diversification. The market centre has to become more attractive for new customers and new traders by offering new possible services.  Some markets could become centres for collecting and disseminating market information, facilitating the dissemination of price knowledge, information on where and when to collect the commodities and how to reduce transaction costs. The traders’ association could have the task of collecting and disseminating information to and from all the other market areas. A service like this could encourage more middlemen, farmers and wholesalers to collect market information directly from the market area and, as a consequence, increase the number of transactions.

The MFIs and other financial service providers could promote the credit system on the main market day by having a small office inside the marketplace. This could give greater visibility to the MFIs  and could attract more customers to the market area.

d)  Creating storage facilities in the areas where there is a surplus of production. This could allow traders to save part of their products and try to obtain a good price from wholesalers. The experience in some project places has shown that the storage facilities are a need expressed by middlemen, traders and farmers.  The opportunity to create a linkage between some marketplaces and stakeholders interested in developing industrial processed food has to be evaluated. For example, there is a surplus of butter production or a surplus of milk or a surplus of honey in a certain market locality that could be used as raw material for agro-industrial processing.

Annexes

Annex A.  Market Infrastructure Development Planning: Criteria for Screening

and Prioritizing Market Centre Improvement Project Proposals

Among rural and urban market places there may be a large number of potential candidates for improvement. At the identification stage it will be necessary to prioritize these so that a realistic improvement programme can be drawn-up. The factors used in the selection criteria and the prioritization process can be given equal weighting, can be ranked (so that a particular factor which is of importance to the development programme can be emphasized) or can be used in a sequential manner to provide a decision tree.

Selection Criteria

The most important criteria for selection of market centres for improvement are

likely to be whether:

- the markets are presently in an unimproved state;

- they have a special function, such as an assembly market (used by producers) or are serving a large rural or urban catchments area.

- they trade in fresh produce (with the majority of permanent and visiting traders selling fresh fruits, vegetables, fish or meat);

- the sites are on land already owned by local government, a market body or authority, or the local community;

- they can be subject to a formal agreement where the developments would be implemented through market committees established with the agreement of the traders;

- there is a willingness on the part of the market traders to improve the efficiency of the present market operations and to accept higher fee or rental charges as a condition of improvements being made;

- assurances have been obtained that adequate financial revenues from the improved markets could be generated to cover operational and maintenance costs and provide funds for further market improvements; and

- the private sector is willing to take responsibility for improving individual sheds and stalls, and the project limits its activities to investment in the upgrading of "common" basic infrastructure, such as:

- site preparation, fencing, parking areas, internal road works and main covered sheds and open sales areas;

- a simple surface/stormwater drainage system, sanitary accommodation and a water supply; and

- garbage collection points, collection carts and shade tree

planting.

Ranking of Market Proposals

Market centre improvement programs are only likely to be viable if the levels of investment are relatively modest. The incremental benefits of undertaking the market improvements should provide sufficient revenues to cover all operating costs, including putting aside a fund for future market expansion. Revenues are often unlikely to be sufficient to cover repayment of capital and interest - even assuming a long repayment period and a grace period before repayment. The returns are very sensitive to the daily charges. Thus, after meeting the selection criteria outlined above, the short-list of proposals should be evaluated and ranked according to:

- whether they make a significant contribution (in terms of volume turnover) to the trading of fresh produce;

- their importance in the overall market system, with priority given to unimproved major markets;

- whether it is possible to use an improved existing market site. A new market site should only need to be considered if it is necessary to replace an existing congested site or if there is an urgent need for expansion because of population growth; and

- whether they comply with the local development planning policy framework:

- the improvements can be linked to other related programmes, such as parallel marketing initiatives, the rehabilitation of rural roads or small-scale civil works (drainage and flood control works, culverts and bridges, in areas adjacent to marketing access roads) that would allow the market to function more effectively;

- the local community is willing to make an undertaking to maintain the facility once it has been improved;

- the selected markets are compatible with areas targeted under a needs-based policy (such as high density areas deficient in services) or a sustainable livelihood approach;

- there is a correspondence with existing lending, donor and NGO programmes;

- there is a lack of alternative funding sources; and

- there is the possibility that a programme of works could be packaged together to form viable construction contracts for a series of market improvements.

Annex B. Data Collection for a Preliminary Survey

It is strongly suggested that for collecting information about physical assets, direct observation, informal discussions with traders and key-informants be used.

1.  Physical Assets

Infrastructures and facilities

- Number and type of physical structures available in the market areas (buildings, mobile stalls, sales platforms, meat/fish sheds, etc.);

- type of activity in each structure;

- existence of a specific area for farmers or wholesale activities;

- zoning of the area by type of products;

- dimensions of the point of sale for each product sold;

- existence of storage facilities for some/all products;

- existence of an appropriate pedestrian crossing;

- existence of an appropriate drainage system;

- existence of an appropriate road for access to the market;

- crowding le el at the marketplace.

Sanitary aspects

- Hygiene condition of the areas and of the entire structure;

- existence of appropriate protection from rain and sun (particularly for perishable products);

- waste disposal;

- water; and

- toilets and their hygiene conditions.

2.  Mapping: (for mapping, working with local experts could be the best option).

- Collect copies of all maps (informal ones, master plans, geographic information system database (if any))

- Conduct a survey if the available maps are not updated (scale 1: 500 of the market area including level details). The site map should include all existing buildings (including illegal ones), infrastructure and facilities

- Verify that the maps are updated

3.  Commercial activities

- volume of goods sold by type;

- transportation system used (bus, mid-size trucks, pick-up, animals, etc.);

- average daily turnover;

- seasonal variation of business volume by type and goods;

- packaging and storage conditions; and

- catchment area for each type of product.

4.   Market management

Public institution (other organization)

- Existence of a market management unit or any entity responsible for market management;

- existence of specific public offices for market management or other offices involved in marketplace activities;

- key persons at the local government level;

- amount of taxes on daily yield/products;

- ordinary maintenance services (i.e. waste management);

- facilities management (water, toilets, electricity, security) if they exist;

Traders

- existence of a market committee;

- existence of any association between market traders;

- the responsibility of market traders for market management (cleaning, security service, maintenance, facilities management, etc.).

5.  Socio-economic situation of market traders

- Number of traders per kinds of product sold;

- average initial capital for each commercial activity;

- number of permanent and temporary traders products sold;

- willingness to increase the tax for market upgrading;

- number of informal traders per products sold;

- traders’ catchment areas; and

- daily transactions.

6.  Farmers and middlemen inside the retail market areas

- farmers’ catchment areas;

- number of middlemen in the market areas;

- type of farmers’ commercial activities (retail or wholesale);

- products provided from middlemen;

- presence of farmers inside market areas (once in a week, daily, etc.);

- type of products sold by the farmers; and

- presence of farmers inside the market areas (once in a week, daily, etc.);

Annex C.   ERIC SPROTT MARKET CENTRE IN BATI, OROMIA ZONE OF Amhara REGIONAL STATE:

A CASE STUDY FOR IMPROVED LOCAL MARKET CAPACITY

The inauguration of the Eric Sprott Market Centre in Bati town took place in February 2009 during the 4th Project Steering Committee meeting of the Partnership for Food Security (PFS-II) Project.   At the initiative of the Administrative offices of Bati woreda and Bati town the market centre was named after Eric Sprott, the Canadian businessman who first provided funding to CHF and the Organization for Relief and Development in Amhara Region (ORDA) in 2003 after a devastating drought placed a large proportion of Bati’s population in a precarious food security situation. The proposed response to address this situation attracted the attention of a Canadian International Development Agency (CIDA) interested in exploring ways to assist vulnerable populations to rise above their chronic dependency on food aid. The initial phase of PFS (PFS-I) responded to the first stages of the relief-to-development continuum while the second phase (under the current PFS-II), which came into being in 2005, focused on its longer-term development potential.  CIDA has provided significant funding to both phases which have targeted  42,000 people in 11 kebeles.

The purpose of PFS-II is to sustainably improve the food security of target households through strengthening agricultural productivity, management and conservation of natural resources, diversification of income, and improving disaster prevention and management capacity. The impact to which the Project aims to contribute is improved food security at household level.

The Eric Sprott Market Centre represents a substantive initial step-forward in supporting market-led development in Bati.  The actual Centre is a building from which 29 vendors (of whom 26 women) sell fresh produce, mosly vegetables.  It has become something of a showpiece because many rural towns do not have such a permanent structure for their market vendors.

CIDA delegation visiting the Eric Sprott Market Centre in Bati, October 2009

At this site previously the vendors sold their produce outside from makeshift shelters completely exposed to the elements, such as wind, sun, dust and rain.  This caused rapid deterioration in the quality of their produce and high rates of spoilage. Moreover, the vendors were always at the mercy of marauding goats constantly attempting to steal meals from the women’s offerings spread out on the ground.

Marauding Goats outside the Eric Sprott Market Centre in Bati

One entrepreneurial vendor, Ansha Mohammed, was recently interviewed in order to know the changes she has seen in her business since moving into the Market Centre.  Ansha Mohammed stated that the marked improvement in the new conditions has caused her income to increase considerably.  Previously when she went to procure her weekly supply of vegetables in nearby Kombolcha she bought on credit which she had to reimburse the following week.

Ansha Mohammed in her stall at the Market Centre, alone and later with a CIDA delegation

Ansha Mohammed further disclosed that after her week’s sales in Bati she sometimes failed to earn, because of high spoilage rates, enough money to allow her to even pay back fully the credit, much less earn a profit to cover other household needs. She now happily states they she uses her own money entirely each time she goes on her purchasing missions and never has to resort to money-lenders. Not only that, but she has augmented her capacity substantially and is mobilizing to continually increase the scope of her business.

Two other female vendors, namely Asres Mokonin and Kasech Teklemariam, were also interviewed. Their stories were similar to those of Ansha Mohammed.  They stated that the conditions in which they work have improved considerably and they are very grateful for this. Previously when they were operating outside they had to pack up their produce and carry it home each day, whereas now they leave it in their stalls at the Market Centre over night.  With this improvement they no longer have to pay labour and transport costs each day.  Despite this, Asres Mekonin still deplores her weak income-generating potential because of her inability to access credit with which to further expand her business.

Asres Mokonin and Kasech Teklemariam at their stalls in Eric Sprott Market Centre, Bati

It is noteworthy that many of the vegetables sold in the market centre come from nearby Kombolcha, not Bati. The vendors must travel about 45 kms each week to renew their inventory.  Their preference is, of course, that these products would be available in Bati because they would not have to pay transport and labour costs to get them to the Market Centre. However, only tomatoes and onions can be obtained in Bati in quantity, and that only for 3-4 months of the year just after the main rainy season.  At the time of preparation of this case-study most of the tomatoes and onions seen in the market centre had been procured from Bati farmers who themselves brought them to Bati town where the women bought them for resale.

Customers who were interviewed and asked about their impressions regarding the quality and price of the produce they purchased unanimously stated that the quality is now better and that prices have not increased, even with the need for the vendors to hire a night watchman to provide security at the market centre.  It is estimated that some 500 customers, on average, avail themselves of the market on a daily basis, depending on the season of the year and their level of buying power during different periods of the year.

Interior view of the Eric Sprott Market Centre, with customers and CIDA delegation

Outside the Market Centre many other vendors are still selling their produce from temporary shelters.  If another centre of the same size were built it would be immediately filled by those wishing to operate inside.  A good variety of fruits produced in Bati, much of it the result of PFS-II interventions, was available in the market at the time of preparation of this case study.  The photo below shows fruits on offer, such as oranges, bananas, guavas, papayas and mandarins, and gives a good indication of the conditions that the vendors now in the Centre used to endure when they were outside.

Fruits for sale outside the Eric Sprott Market Centre in Bati

In conclusion, the presence of the Eric Sprott Market Centre represents a great advancement in Bati town’s capacity to provide its citizens with clean, high-quality fresh produce.  High satisfaction levels prevail amongst both customers and the vendors themselves whose businesses are increasing in size and scope.  Moreover, the quality-of-life improvements for the women operating from the Market Centre are palpable: with their augmented incomes their overall livelihoods are enhanced.  They state proudly that they are now better able to provide for the regular needs of their families: more nutritious food, health costs and school fees.  However, the greatest contribution made by the Market Centre to the lives of these women is perhaps the trend towards an enhanced sense of empowerment they experience as their incomes, and thus social standing, increase.  This phenomenon will no doubt continue to grow over time as Bati farmers exploit more fully the opportunities they have garnered from their association with PFS-II and are able to avail the vendors at the Market Centre with greater quantities of locally produced commodities.

Annex D.     List of Further Reading

FAO, 1995. Retail markets planning guide, FAO Agricultural Services

Bulletin No. 121, FAO, Rome.

FAO. 1999. Market infrastructure planning: a guide for decision makers, by J. Tracey-White. FAO Agricultural Services Bulletin No. 141, Rome.

FAO. 2003. Planning and Designing Rural Markets, by J.D. Tracy-White, FAO Marketing Extension Guide No. 4, Rome.

German Federal Ministry for Economic Cooperation and Development (BMZ), 1995. Environmental Handbook: Documentation on Monitoring and Evaluating Environmental Impacts Volume 1.

Italian Cooperation ABRDP. 2006. Report on Market Rehabilitation Project, Arsi Bale Rural Development

Project, Asella.

Italian Cooperation ABRDP. 2007. Report on Market Rehabilitation Project, Arsi Bale Rural Development

Project, Asella.

Ministry of Agricultural and Rural Development (MoARD), 2000. Agricultural Input and Product Marketing Strategy and Implementation Mechanism, Ethiopia, Addis Ababa.

Ministry of Finance and Economic Development (MoFED), 2006. Plan for Accelerated and sustainable Development to End Poverty (PASDEP), Ethiopia, Addis Ababa

Ministry of Agriculture and Rural Development (MoARD), 2009. Community Level Participatory Planning Process Guideline, Agricultural Growth Program (AGP) guideline document, Ethiopia, Addis Ababa.

World Bank, 2009. Project Implementation Plan (PIP), Agricultural Growth Program (AGP), The World Bank, Ethiopia, Addis Ababa.

World Bank, 1991. Environmental guideline for rural projects, Environmental Assessment Sourcebook, USA, Washington D.C.