UCM ICT Strategy Paper – 2008 draft 1

Introduction

…

A. Document Development Process

After seeing the ever rising need of a systematic organization of the use of ICTs in UCM the Magno Vice Chancellor and Rector appointed an ICT UCM Committee on 21 May 2008 through his decree number 21.05.08/INF/REIT. The ICT UCM Committee was consisted of Dean of Faculty of Economics and Management as Chairperson, Information and Communication Technology Director as the Secretary, Information Technology Course Coordinator from Pemba Faculty, Information Technology Course Coordinator from Beira IT course and the UIS Manager.

In the preliminary phase a work plan and budget to support the elaboration of the ICT Strategic Plan, which was approved on 27th of June 2008. Literature review was carried out which saw the analysis of different strategic plans from universities like Makere of Uganda, National University of Science and Technology of Zimbabwe, Universidade Eduardo Mondlane of Mozambique, UCM general strategic plan, the ICT policy in Mozambique and the document by the Council for the Development of Social Science Research in Africa.

The development of the UCM ICT Strategic Plan was inspired by the UCM general strategic plan objectives (See Annex 01) and its statutes which reiterate on the use of modern innovative methodology of study basing on the use of advanced technology. This will go a long way to contribute to the guarding of the reputation so far achieved.

After the preliminary phase a situational analysis was carried out where each faculty had an opportunity of discussing their current ICT status and how they want their ICT to be like in three years time. This process was coordinated by faculty ICTs and several reports were produced. The reports were synthesized into one shown in Annex 02. The analysis and synthesis of the individual faculty reports provided an analysis of UCM strengths, challenges, opportunities and threats (SCOT) with respect to information and computing technologies (ICT).

A six days workshop was held and resulted in the first draft of the UCM ICT Strategic Plan and way forward.  A presentation of the first draft to the Rectorate was done and the first approval in principal was obtained. More consultations will take place and the document will be discussed during the University Council meeting in August 2008. The objective of the strategic plan is to create an academic environment at UCM that encourages application of ICT systematically and innovatively in teaching and learning, research, community service, administration and management. The major outputs of the plan are an integration of ICT into UCM strategic plan, use of ICT in teaching and learning and research activities by academics and students, integrated and computerized management systems for key administrative functions at UCM, improved ICT infrastructure and networks, promote outreach using ICT and improved ICT services in general by training of ICT personnel.

B. Current situation

Here we are going to make some important conclusions and observations, while the detailed current status (with numbers) of the ICT in UCM is presented in Annex 02.

B.1. Internet Connectivity

All faculties and centers are connected to the Internet except Faculty of Economics and Management in Tete. The best connectivity at the lowest rates is TDM´s Broadband which is 2mbps download and 512kbps upload at a cost of 5,400.00 meticais per month. These solutions are currently running in UCM faculties in Beira. The lowest being FEG Chimoio and FAgrc in Cuamba with 128kbps download and 64kbps upload. Chimoio uses TDM whilst Cuamba uses Teledata and the monthly costs are 899.00 and 1,500.00 meticais respectively. FEG Chimoio can upgrade their connectivity to 2mbps download and 512kbps upload whenever the need to do so arises. The most expensive of them all is satellite connection of FGTI Pemba with 1mbps download and 128kbps upload paying a monthly fee of 19,750.00 meticais to Geolink of France.

There are four ISPs being used in different UCM campuses, which are TDM (Beira and Chimoio), Bently Walker (Nampula), Teledata (Cuamba) and Geolink (Pemba).

B.2. Hardware

The last voluminous batch of 450 second hand computers arrived in Pemba in 2006 which were successfully distributed to all existing faculties and centers. The computers came as a short term solution to replace the old Pentium IIs which were in use by that time. These 450 second hand computers from the USA had already a life spun of two to three years old, which means by now the majority of the computers in use in all UCM faculties and centers except in FEC (with 53 computers less than two years old and 44 more than two years old) are more than five years old. The other observation is about the laptops and projectors, as the table on Hardware in Table 02 in Annex 02 shows. The number has reduced from 450 to 282 because of breakdowns. The breakdowns are difficulty to recover because the spare parts are not available on the local market.

B.3. Software

The operating system running on our user computers is mainly Windows 2000 Professional (265 computers) against 133 computers with Windows XP Professional SP2 and 7 running Linux.

On the following Information Systems we have,

- e-learning - KGen, at this time only used at FGTI,

- library - Winnebago for all except FDIR and CED who use Access and Excel respectively,

- student registration system - OpsCollege for all except FDir & FEC and CED who use Access and Excel respectively,

- accounting and human resources - Primavera and pay roll, the latter not being used.

UCM has 22 servers currently working in all faculties and centers. 10 of them are running Windows 2003, 10 are running Linux and the rest is running Windows 2000 Server software. UCM practically do not have Database and Webserver applications. The antivirus software being used is F-Secure and there is no encryption implemented.

B.4. Network Infrastructure -LAN

All faculties and centers have functioning local area networks (LAN) except for FEG Tete. All the six faculties´ LANs have a fiber optic backbone which in all cases is not being used. A wired area network is in the process of being installed in CED. Wireless network only exist in FGTI and CED.

C. SCOT ANALYSIS

The UCM situation may be represented by having a look at the strengths, challenges, opportunities and the threats that the university may have.

C.1. Strengths

The following have been noted as some of the strengths for UCM

- Geographic Location –UCM is spread over a very wide geographic area that includes Sofala, Manica, Tete, Nampula, Niassa and Cabo Delgado provinces. Plans are underway to have campuses in Zambezia and City of Maputo (Annex 03). The campuses are located in the provincial capitals except in Niassa Province where the Faculty of Agriculture is situated in the district capital of Cuamba. Once UCM establishes an intranet, UCM might consider offering services to interested companies and organization for  an efficient use of the infrastructure.

- UCM Christian values – UCM has been driven by its human and social values which are reflected in its mission and stand firm for its fight against inequality, discrimination and corruption.

- Reputation – UCM is among the best known universities in Mozambique and lives up with its slogan “Quality & Innovation”. The use of ICT in UCM is therefore on of the fundamentals.

- Teaching Methodology – UCM is well known for its teaching methods blend. UCM has adopted a teaching methodology which pre-dominates Problem Based Learning supported by the traditional teaching methodologies. This has seen the development of a great sense of ownership and responsibility by the students. The independence created in students will help them to easily learn how to use the ICT tools on their own with little assistance. The use of ICT may help to consolidate these efforts.

- Bi-lingual teaching – UCM has adopted the use of English and Portuguese as the languages of instruction. Students are required to have a certain level of proficiency in English which facilitates the integration of the graduates produced by UCM into labour markets and as well for those who seek to pursue their studies further elsewhere in the world. On the other hand this is an advantage when learning how to use ICT tools as most of these come in English.

C.2. Challenges

Besides the strengths UCM will experience the following ICT-related challenges:

- Very old and inadequate equipment – As shown in the current UCM situation above, most of the ICT equipment is old, hence inadequate because of lack of spare parts to repair the faulty old equipment.

- Non existence of an Intranet – As it is noted that UCM´s geographic spread (Annex 03) is on one hand a strength it may be considered as well as a challenge. UCM do not have an intranet and establishing one may be a big challenge as UCM campuses are widely spread as mentioned above.

- Various internet connections – Because of the geographic location of UCM campuses a number of Internet solutions are conveniently used so as to give a temporary solution to the Internet connectivity problems. This is not an optimum situation which will be required to improve in future by using only one ISP and one type of connectivity (ADSL or Satelite).

- Lack of central control and planning – Taking into account the expansion plans, UCM needs to have sufficient ICT personnel so that the ICT coordinator can dedicate sufficient time on his management duties.

- Inadequate ICT support skills – Most of the ICT support staff are recent graduates of UCM. To produce quality in support and maintenance of the ICT equipment, ICT teams may consist of technicians at medium and higher education level. Skills profiles and timely capacity building of ICT support staff needs to be done in collaboration with the Faculties and the Human Resources Department.

- Lack of (ICT) staff development plan – Due to the expected rapid growth of IT and ICT, as well as the competitive environment, UCM needs to address career planning within its overall HR policy and HR development plan. Responsive remuneration schemes and formation profiles for ICT staff retention need to be elaborated and put into force.

- Inadequate funding for ICT projects – It is not yet a common practice at UCM to place maintenance and replacement of ICT equipment on regular faculty budgets and ICT investments are partly supported by a major capacity building project (Nuffic/NL). ICT related expenditures need to be incorporated into the annual budgeting process and our efforts to have up-to-date ICT facilities in all our locations will need some external funding (donor/government program support).

- Manual administrative processes – Most of the administrative processes are manual due to lack of an intranet. With the establishment of the intranet this may be set to improve.

- Low utilization of ICTs in teaching and learning –Provision of ICT tools to support teaching and learning is imperative. Distance learning is proofing already an product in great demand and the introduction of e-learning will become over the years an important tool to reach more people at reduced transaction costs. This is supposed to be accompanied by tailored user training on both sides.

C.3. Opportunities

- Ability to increase student numbers through e-learning –The use of ICT may facilitate the increase of students’ enrolment through the use of tools like e-learning which can enhance the distance education programs. With the increase of number of students an opportunity to have a better ICT budget becomes more promising.

- Local and regional e-initiatives – The use of e-learning will facilitate UCM to make strong local and regional impact. In future students and clients may as well enroll for a UCM course module or an entire course. Our policy on quality and innovation opens a credible role to contribute to set regional standards for quality and transparency in this segment.

- Technology Savvy students

- Donor support for new technology – Despite the general tendency for governmental budget support there is an opportunity to explore donors regarding the technology aspect for development and the role of UCM in Mozambique as an active member in some key programs of the MEC.

- Falling prices of technology – UCM may benefit from falling prices of technology to up-grade and successfully keep its ICT facilities on an adequate level.

C.4. Threats

- Competition – There is increased competition from other universities offering similar academic courses as well as a wide range of commercial products and training seminars. Therefore future students and customers will have improved local access and more choice.

- Inadequate physical infrastructure – UCM needs to make sure that infrastructures like intranet, internet access and adequately equipped training centers (ICT laboratories) are available in all our locations.

- Staff turn over – Staff turn over has been partly caused by the lack of ICT professionals in the market. Better working conditions (that should result partly with the implementation of the ICT strategy plan) needs to be put into place to encourage staff retention. On the other hand UCM may create among its students a pool of future ICT technicians.

- Lack of student scholarships – UCM currently does not have a student scholarship scheme, depending on partnerships and individual donations. With public universities offering an increased number of highly subsidized vacancies in IT/ICT technologies, this may be seen as serious threat in the near future.

D. Strategic Objectives

D.1. Vision

A university-wide access to, and utilization of information and communication technologies to enhance the position of the Catholic University of Mozambique (UCM) as a leading university with countrywide presence and/or accessibility.

## D.2. Broad Strategic Objectives

- Teaching and Learning: Improve and develop innovative ways of teaching and learning and student assessment based on ICT.

- Management: Enhance administrative effectiveness and efficiency through use of integrated and computerized management systems

- Infrastructure: Implement and maintain reliable and fast campus networks and links to the internet

- Staff Development: Raise appropriate competencies in use of ICT by all staff

- Research and Community Development: Enhance research and community development through accessibility and application of ICT tools and facilities.

D.3. Specific strategic objectives

D.3.1Teaching and Learning: Improve and develop innovative ways of teaching and learning and student assessment based on ICT

On its pursuit to become a reference of academic excellence, UCM prioritize the use of innovative ways of teaching, learning and students assessment based on ICT. A high degree of accessibility to information and learning materials is rated within the top two by UCM and ICT has been identified as the main tool to achieve this. To accomplish this strategic objective the following specific objectives have been drawn:

D.3.1.1. Create and put teaching and learning material on the Web

This aims in optimizing the use of available facilities for teaching, learning and student assessments in innovative ways. The use of ICT tools has been adopted at UCM in different speed and a non-formalized way and – with the introduction of e-learning based courses - lecturers have to change from the traditional way to the identified one. With UCM’s promise on quality and innovation, it is imperative that any new form or method is carried and applied by its academic staff by using the respective tools and techniques in their day to day professional duties performance as required. With an increased offer of e-learning (presence or distance courses) this process will include the development and putting of teaching and learning materials on the Web or e-learning platform so as to facilitate its access by students from anywhere. In order to achieve this objective the ICT Department has to provide the necessary input for the UCM website and the e-learning platform.

D.3.1.2. Enable effective use of ICT by students

It is of high priority that all UCM students be able to use the ICT facilities effectively and efficiently to enhance high quality learning and hence contribute significantly to becoming reputable professionals in their future jobs (in line with UCM mission). This specific strategic objective guarantee that the learning materials placed on the Web or e-learning platform be accessed by students, hence the need of training needs to be addressed. In this respect UCM students will be trained in use of web-based learning materials and on use of computerized Library system. All students will undergo the necessary computer skills training as an integral part of their curriculum. The ICDL courses have already been identified and adapted by UCM as standard computer skills courses. Some orientation on how to use the library system and how to access content on the university website & on the e-learning system will also be included.

D.3.1.3. Summary Matrix

| Specific Strategic Objectives | Strategic Action | Leader/ Implementer | Target/ Date | Indicators | Initial Cost | Recurrent expenditure |
| --- | --- | --- | --- | --- | --- | --- |
| Create and put teaching and learning material on the Web | Develop and put teaching and learning material on the Web | V. Rector Academic/ Pedagogical Dir. | August 2009 | 90% of the modules at each faculty have outlines online 20% of the modules at each faculty have content online | 40000 |  |
|  |  |  | August 2010 | 50% of the modules at each faculty have content online | 50000 |  |
|  |  |  | August 2011 | 90% of the modules at each faculty have content online | 50000 |  |
| Enable effective use of ICT by students | Train all students on ICDL and on how to use the e-learning platform | Pedagogical Dir | August 2010 | a. All first year students complete ICDL b. All Students trained on how to use the e-learning platform | 20000 | 10000 |

## D.3.2. Management: Enhance administrative effectiveness through use of integrated and computerized management systems

Whilst the teaching and learning is the core business of UCM, it has been observed that good management is a key to success. To achieve good management there is a need to have smooth information flow which is in turn facilitated by modern Information Technologies. Considering the challenge that UCM is a nationwide provider of HE, currently present in six provinces in the Central and Northern Regions of Mozambique and an expanding distance education program (Annex 03), it is important to come up with a tool that facilitates the smooth flow of information in real time in a cost effective way. In order to assure ICT to provide functional services, the following objectives are listed:

D.3.2.1. Computerize and integrate library, student, finance, assets and personnel records

The management is in constant handling of essential information about student, library, finance, personnel and assets, hence automating these records is inevitable. Automated electronic information management systems for library, student, personnel, financial and assets records are acquired and implemented. The software will be updated regularly for efficient management of the institution and easy access to data for executive decision making will be guaranteed.

D.3.2.2. Implement systems that secure data and information from unauthorized access and tempering

Taking into account the UCM automating process mentioned above, information and data security becomes a critical issue. The nature of UCM spatial spread implies having an Intranet that relies on support of other infrastructures that belongs to other companies or institutions. The ICT Department will be compelled to put in place security measures that minimize the risks of system disruption and unauthorized access. A good password policy will be implemented. A reputable anti-virus and encrypting software will be installed all over the UCM Intranet.

D.3.2.3. Improve information accessibility

There is a need of improving how users have continuous access to information. In the first place it is imperative that users be given easy access to use platforms. In this respect a user friendly platform for web content management using the latest technology will be provided. At the same time the university will implement an electronic document management system for timely institutional distribution of documents. Key users will be encouraged to use electronic diaries and meeting schedulers. In second place UCM intends to make sure that users connection to relevant e-resources will continue even off-campus.

D.3.2.4. Develop and enforce ICT policies

To guarantee accomplishment of this strategic plan, it will be of great importance to develop and enforce the following policies:

- ICT Services and systems Policy

- Information systems policy

- E-learning Policy

- Data communication and infrastructure policy (acquisition, deployment and disposal of ICT hardware and software)

- ICT management policy

- Common data services and office automation policy

These policies go in line with the five identified key areas in this document.

D.3.2.5. Summary Matrix (including information regarding funding status/sources)

| Specific Strategic Objectives | Strategic Action | Leader Implementer | Target/Date | Indicators | Initial Cost source | Recurrent Expenditure status/source |
| --- | --- | --- | --- | --- | --- | --- |
| Computerize and integrate library, student, finance, assets and personnel records | Implement student registration system | UIS Manager | November 2008 | 50% of all faculties and center. | 5000 | 5000 (server outsourcing) |
|  |  |  | November 2009 | 100% of all faculties | 10000 |  |
|  | Implement alumni system |  | February 2009 | Alumni system is implemented | 3000 |  |
|  | Implement appropriate LIS | Chief Librarian | August 2009 | 50 % of all faculties | 20000 |  |
|  |  |  | August 2010 | 100% of all faculties | 20000 |  |
|  | Implement finance management system | Accounting Consultant (Irmgard) | December 2008 | 50% of faculties produce monthly accounting reports | 10000 |  |
|  |  |  | December 2009 | 100% of faculties produce monthly accounting reports | 15000 |  |
|  | Implement the HR system | Director HR | December 2008 | 50% of all HR records in system | 7000 |  |
|  |  |  | August 2009 | 100% of all HR records in system | 15000 |  |
|  | Implement the asset management system | ERP Specialist (Andreas) | December 2008 | GIS and FMED assets recorded in system | 7000 |  |
|  |  |  | December 2009 | 50% of all asset records | 15000 |  |
|  | Implement the payroll system | Vice Rector Finance & Administration | August 2009 | 25% of faculties | 10000 |  |
|  |  |  | December 2010 | 100% of faculties | 15000 |  |
| Implement systems that secure data and information from unauthorized access and tempering | Implement data security policy | ICT Director | December 2008 | Policy implemented | 30000 | 20000 |
|  | Implement University wide Central Authentication system | ICT Director | July 2009 | Central Authentication system is in place | 5000 |  |
| Improve information accessibility | Provide a user friendly platform for web content management | ICT Director | December 2008 | All needed content management features are enabled | 3000 |  |
|  | Implement an electronic document management system | ICT Director | December 2008 | document approvals functionality is available | 3000 |  |
|  | Generate appropriate content | Public Relation Manager | December 2008 | Monthly updates of web content |  |  |
| Develop and enforce ICT policies | Produce the following draft policy documents: - ICT Services and systems Policy - Information systems policy - E-learning Policy - Data communication and infrastructure policy - ICT management policy - Common data services and office automation policy | ICT Committee Chair | August 2008 | Draft policy documents developed | 8000 |  |
|  | Approval and adoption of the final draft of the ICT policies | Rector | August 2008 | ICT policies approved |  |  |
|  | Dissemination of the ICT policies | Director of ICT | September 2008 | Policy with all ICT users of the whole UCM |  |  |
|  | Implement the ICT policies | Director of ICT | October 2008 and there after | ICT policies implemented and enforced |  |  |
|  | Review of the ICT policies | ICT Committee Chair | 5 December 2008 | Revised ICT Policies | 7500 |  |

## D.3.3. Infrastructure: Implement and maintain reliable and fast campus networks and links to the internet

The accomplishment of the above objectives depends on how fast and reliable are the campus networks and links to the Internet. To begin with, putting in place a UCM intranet is essential and should be considered as one of the biggest challenges. The wide geographic area covered by UCM (Annex 03) makes it unavoidable the use of other players´ infrastructures. There will be need of use of one ISP. On the other hand UCM will make sure that all its Faculties and Centers have:

- Good Internet access connectivity,

- Campus networks installed

- Adequately equipped ICT teaching labs established

- ICT multimedia teaching equipment for lecture rooms available

- Wireless Networks installed

- Adequately equipped learning centers established

- Adequately equipped  Libraries with ICT resources

- A Student Computer Ownership Scheme (SCOS)

- A Help-Desk and an On-Site support system established

- Incorporate ICT in regular annual budgeting proess

## D.3.3.1. Summary Matrix

| Specific Strategic Objectives | Strategic Action | Leader/ Implementer | Target/Date | Indicators |  | Budget Estimate |
| --- | --- | --- | --- | --- | --- | --- |
| Develop a University intranet (Faculty interconnection network) | Develop the UCM intranet project | ICT Director | December 2008 | UCM intranet project document | 6,000 |  |
|  | Approval of the UCM intranet project | Rector | January 2009 | Approved project document |  |  |
|  | Implement the UCM intranet design | ICT Director | December 2009 ?? | 50% UCM intranet developed | 120,000 | 50,000 |
|  |  |  | June 2010 ?? | 80% UCM intranet developed |  |  |
|  |  |  | December 2010 ?? | 100% UCM intranet developed |  |  |
| Ensure that all UCM Faculties and Centers have harmonized Internet access | Connect all UCM Faculties and Centers to the Internet | ICT Director | December 2009 ?? | 100% UCM connected to the internet by one ISP |  |  |
| Install Campus networks in all UCM Faculties and Centers | Install standard based local area networks in all UCM | ICT Director | June 2009 | 100% all UCM faculties and centers have LAN | 100,000 (10K per center) | 10,000 (1k per center) |
| Adequately equip teaching labs in all UCM Faculties and Centers | Purchase adequate equipment for teaching labs in UCM Faculties and Centers | Vice Rector Finance and Administration | On-going starting January 2009 | 300 computers are purchased per annum |  | 300,000 |
| Adequately equip all academic and administrative staff | Purchase adequate equipment for staff | Vice Rector Finance and Administration | On-going starting January 2009 | 50 computers purchased per annum |  | 60,000 |
| Equip adequately, the Library with ICT resources | Purchase adequate ICT equipment for library in UCM Faculties and Centers | Vice Rector Finance and Administration | On-going starting January 2009 | 20 computers purchased per annum |  | 20,000 |
| Promote a Student Computer Ownership Scheme (SCOS) | Establish a student computer ownership scheme | Rector | June 2009 | 10% of UCM students benefit from the scheme | 20,000 | 10,000 |
| Establish a Help-Desk and an On-Site support system | Develop a Help-Desk, an On-Site support and Preventive maintenance | ICT Director | December 2008 | A Help-Desk workflow process and all the associated forms are in place |  |  |
|  |  |  | July 2008 | A preventive maintenance schedule is in place in all UCM faculties and Centers |  |  |
|  |  |  | June 2009 | A full functional Help-Desk | 1,000 | 6,000 |

## D.3.4. Staff Development: Raise appropriate competencies in use of ICT by all staff

Along side with UCM becoming one of the most computerized universities, it is of high importance to raise competencies in use of ICT by all staff. This implies training of users (staff) and capacity building of technical staff. The following specific strategic objectives have been drawn:

D.3.4.1. Enable effective use of ICT by lecturers

To guarantee the effective use of ICT, in particular web-based learning material development and use of computerized teaching materials by lecturers; training of lecturers in these areas will be conducted. This aspect will be policy driven with all lecturers having equal opportunities of access to relevant computer skills training.

D.3.4.2 Enable effective use of Information Systems

On the other hand, staff will be trained in the use of some Information Systems and other relevant application software. Training needs will be identified and lecturers will be trained in phases through workshops. It is of high importance that UCM staff be computer literate enough to dominate and use the Information Systems (for example like Outlook for communication, planning and scheduling).

D.3.4.3 Enable effective support of the ICT infrastructure

One of the most important aspects in training is the timely and continuous training of the ICT support staff. As the university grows in ICT use, it is imperative to have technical staff that is capable of keeping the systems and services running through high quality maintenance. In this sense all ICT staff will be trained in all relevant areas in order to effectively support the ICT systems (Infrastructure and software).

D.3.4.4. Summary Matrix

| Specific Strategic Objectives | Strategic Action | Leader/ Implementer | Target/Date | Indicators | Budget | Recurrent Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Enable effective use of ICT by lecturers | Train lecturers in developing web-based learning materials and on use of computerized teaching materials. All lecturers have access to relevant computer skills training. | V. Rector Academic and Development | June 2009 | 80% of the academic staff is trained | 20,000 | 20,000 |
|  |  |  | December 2009 | 100% of the academic staff is trained |  |  |
| Enable effective use of Information Systems | Build local capacity to support the University Information Systems | UIS Manager | December 2008 | Support staff is identified (E-learning, Primavera, ARIS) | 15,000 | 5,000 |
|  |  |  | December 2009 | Support staff trained for each UIS |  |  |
|  | Achieve Local staff Software Developer level competence |  |  | 2 Local staff Software Developers trained | 10,000 | 5000 |
| Enable effective support of the ICT infrastructure | Build local capacity to the ICT support staff | ICT Director | December 2008 | ICT support staff training programme | 100,000 | 10,000 |
|  |  |  | January 2009 | ICT support staff training programme is implemented |  |  |

## D.3.5. Research and Community Development: Make ICTs available to research and community development

UCM is a social driven university, orientated by Christian values and based on its statutes with a clear mission that includes this social and human aspects. To facilitate this academic and social mission, the following specific strategic objectives have been drawn:

D.3. 5.1. Develop a platform for outreach

UCM wants to strengthen the community-university relationship already built through the increased use of ICT. UCM will provide a platform for delivery of:

- Initiatives and courses on continuing education in issues such as AIDS/HIV, business skills for micro and small enterprises in both the formal and informal sector, environment management, disaster management, etc. at community level,

- Initiatives and information of the “Pastoral Universitário” and other important UCM social policies on subjects like HIV/AIDS, sexual harassment and corruption,

- Know-how and tools based on agreements established between UCM and Dioceses how to use best new technologies.

D.3.5.2. Facilitate research and dissemination of research results through the use of ICTs

One of the important issues will be to facilitate research and the dissemination of research results. Lecturers, students and some members of the community will have access to international journals and UCM research reports A UCM portal that facilitates this access will be created.

D.3.5.3. Summary Matrix

| Specific Strategic Objectives | Strategic Action | Leader/ Implementer | Target/Date | Indicators | Budget | Recurrent Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Develop a platform for outreach | Provide training and support to the “Pastoral Universitário” | ICT Director | June 2009 | University caplans are familiar with e-platform and promote social policies and pastoral initiatives | 1000 | 1000 |
|  | Provide a platform for Outreach courses | UIS Manager | June 2009 | A platform for outreach is developed | 1000 | 1000 |
| Facilitate research and dissemination of research reports through the use of ICTs | Provide a portal for access to journals and research reports | Chief Librarian | December 2009 | A portal for access to international journals and research reports is developed | 10000 | 2000 |

D.4. Budget Summary

| Item | Initial Cost (USD) | Recurrent Cost (USD) |
| --- | --- | --- |
| Teaching and Learning | 60000 | 60000 |
| Management | 205500 | 25000 |
| Infrastructure | 253000 | 520500 |
| Staff Development | 145000 | 40000 |
| Research and Community Development | 12000 | 4000 |
| TOTALS | 675,500.00 ??? | 649,500.00 ??? |

Comment: Status and sources of funding to be incorporated (for a more realistic picture)

Annexes

Annex 01

# UCM Strategic Objectives 2007-2010 extracted from UCM Strategic Plan

Os objectivos estratégicos da Universidade Católica de Moçambique para o período 2007-2010 são:

- consolidar e fortalecer a sua identidade Católica,

- lutar pela eficiência administrativa e sustentabilidade financeira através do aumento do número de cursos, estudantes e nível de prestação de serviços,

- adequar os graus académicos e métodos de ensino às exigências e realidade moçambicana;

- desenvolver e estabilizar o quadro dos recursos humanos,

- melhorar as condições de trabalho e sociais dos docentes, trabalhadores e estudantes;

- desenvolver as infra-estruturas físicas e tecnológicas e a expansão geográfica para as províncias de Tete, Zambézia, Manica e Maputo.

## Objectivos prioritários

Constituem prioridades da UCM os seguintes objectivos e iniciativas:

- O fortalecimento da identidade católica da UCM através da revitalização da Pastoral Universitária e outras actividades de carácter religioso;

- Alcançar sustentabilidade financeira através do aumento de números de ingressos, serviços prestados e utilização racional dos recursos existentes;

- Introdução de um plano de carreira profissional, que inclui salários competitivos e outros benefícios, para a estabilização do corpo docente, pessoal técnico-administrativo e pessoal de apoio;

- O relançamento das Faculdades com a introdução de novos cursos;

- Estudar a possibilidade de manutenção ou revisão da estrutura Bacharelato-Mestrado vis à vis a estrutura Bacharelato-Licenciatura-Mestrado;

- Estudar a possibilidade da revisão em algumas Faculdades do uso da língua inglesa como a língua solitária de ensino;

- Construir casas para docentes particularmente em Pemba;

- Construir lares para estudantes;

- Estudar a viabilidade da abertura de uma Faculdade de Engenharias (Chimoio), Faculdade de Mineralogia (Tete), Faculdade de Ciências Políticas (Zambézia), Faculdade de Filosofia e de Teologia (Maputo).

Annex 02: Current Situation Analysis

Table 01: Bandwidth

| Faculty | Bandwidth |  | Cost (Mts) | Type | Reliability | Service Provider |
| --- | --- | --- | --- | --- | --- | --- |
|  | Down | Up |  |  |  |  |
| FEG | 2mbps | 512kbps | 5,400.00 | ADSL | Acceptable | TDM |
| FEG Chimoio | 128kbps | 64kbps | 899.00 | ADSL | Acceptable | TDM |
| FEG Tete |  |  |  |  |  |  |
| FMed | 2mbps | 512kbps | 5,400.00 | ADSL | Acceptable | TDM |
| FGTI | 1mbps | 128kbps | 19,750.00 | V-Sat | Acceptable | Geolink |
| FEC |  |  |  |  |  |  |
| FDir | 1mbps | 512kbps | 15,026.67 | V-Sat | Acceptable | Bentley Walker |
| FAgric | 128kbps | 64kbps | 1,500.00 | ADSL | Acceptable | Teledata |
| CED | 512kbps | 256kbps | 2,564.00 | ADSL | Acceptable | TDM |

Table 02: Hardware

| Faculty | PC |  | Laptops |  | Printers |  | Projectors |  | Scanners |  | Data banks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | <2 yrs | >=2 yrs | <2 yrs | >=2 yrs | <2 yrs | >=2 yrs | <2 yrs | >=2 yrs | <2 yrs | >=2 yrs | <2 yrs | >=2 yrs |
| FEG FEG Chimoio | 8 | 56 | 4 | 2 | 7 | 3 | 2 |  | 2 | 1 |  |  |
|  | 4 | 30 | 2 | 1 | 4 | 1 | 1 | 1 | 0 | 0 | 1 | 0 |
| FEG Tete | 4 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |
| FMed | 57 | 12 | 1 | 2 | 5 | 5 | 1 | 4 | 0 | 2 | 4 | 4 |
| FGTI | 4 | 39 | 1 | 2 | 2 | 7 | 1 | 2 | 1 | 0 | 4 | 0 |
| FEC | 53 | 44 | 7 | 0 | 4 | 4 | 0 | 2 | 1 | 1 | 4 | 0 |
| FDir | 3 | 53 | 0 | 0 | 5 | 2 | 1 | 0 | 1 | 1 | 4 | 0 |
| FAgric | 3 | 40 | 0 | 1 | 1 | 6 | 0 | 1 | 2 | 0 | 4 | 0 |
| CED | 6 | 8 | 5 | 2 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 0 |

Software

Table 03: Workstations (Operating system)

| Faculty | Win 98 | Win 2K | Win XP | Win Vista | Linux |
| --- | --- | --- | --- | --- | --- |
| FEG | 1 | 10 | 53 | 0 | 0 |
| FEG Chimoio | 0 | 30 | 5 | 1 | 0 |
| FEG Tete | 0 | 0 | 6 | 0 | 0 |
| FMed | 0 | 62 | 34 | 2 | 2 |
| FGTI | 0 | 29 | 3 | 1 | 2 |
| FEC | 0 | 38 | 18 | 0 | 1 |
| FDir | 0 | 54 | 2 | 0 | 0 |
| FAgric | 0 | 30 | 10 | 1 | 2 |
| CED | 0 | 12 | 2 | 7 | 0 |

Table 04: Servers

| Faculty | Operating System |  |  |  | Applications |  | Security |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Win2K | win2003 | Win2008 | Linux | Database | Webserver | Antivirus | Encrytion |
| FEG | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |
| FEG Chimoio | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 |
| FEG Tete |  |  |  |  |  |  |  |  |
| FMed | 2 | 2 | 0 | 1 | 0 | 0 | 1 | 0 |
| FGTI | 0 | 2 | 0 | 3 | 2 | 0 | 1 | 0 |
| FEC | 0 | 2 | 0 | 3 | 0 | 0 | 1 | 0 |
| FDir | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 |
| FAgric | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 |
| CED | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |
|  | 2 | 10 |  | 10 |  |  |  |  |

Table 05: University Information System

| Faculty | Email | Elearning | Library | Students Registration | Accounting | Human Resources | Payroll |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FEG | 0 | 0 | winbago | Ops College | Primavera | Primavera | 0 |
| FEG Chimoio | 0 | 0 | winbago | Excel | 0 | 0 | 0 |
| FEG Tete |  |  |  |  |  |  |  |
| FMed | 0 | 0 | winbago | Opus-College | Primavera | Primavera | 0 |
| FGTI | 0 | Kewl | Winbago | Opus-College | Primavera | Primavera | 0 |
| FEC | 0 | 0 | winbago | Access | Primavera | Primavera | 0 |
| FDir | 0 | 0 | Access | Access | Primavera | Primavera | 0 |
| FAgric | 0 | 0 | winbago | Opus-College | Primavera | Primavera | 0 |
| CED | 0 | 0 | Excel | Excel | Excel | 0 | 0 |

Table 06: Network Infrastructure -LAN

| Faculty | Backbone |  | Data points | Wireless | 3 com switches | Cisco Switches | Others | Modems | Firewalls |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fiber | UTP |  |  |  |  |  |  |  |
| FEG | yes | yes | 58 | No | 6 | 0 | 0 | 1 | 0 |
| FEG Chimoio | No | Yes | 65 | No | 2 | 0 | 0 | 1 | 0 |
| FEG Tete |  |  |  |  |  |  |  |  |  |
| FMed | yes | yes | 136 | No | 6 | 0 | 0 | 1 | 0 |
| FGTI | yes | yes | 75 | Yes | 4 | 5 | 3 | 1 | 0 |
| FEC | yes | yes | 121 | 0 | 3 | 0 | 2 | 1 | 1 |
| FDir | yes | yes | 124 | 0 | 0 | 0 | 3 | 1 | 1 |
| FAgric | No | Yes | 53 | 0 | 4 | 0 | 0 | 2 | 0 |
| CED | No | No | 0 | Yes | 1 | 0 | 0 | 1 | 0 |

Table 07: Current ICT department HR

| Faculty | Qualification |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | Non graduates | BSc | Licentaites | Masters | PhD |  |
| FEG | 0 | 1 | 1 | 0 | 0 | 2 |
| FEG Chimoio | 1 | 0 | 0 | 0 | 0 | 1 |
| FEG Tete | 0 | 0 | 0 | 0 | 0 | 0 |
| FMed | 0 | 1 | 1 | 0 | 0 | 2 |
| FGTI | 1 | 0 | 3 | 0 | 0 | 4 |
| FEC | 0 | 2 | 1 | 0 | 0 | 3 |
| FDir | 1 | 1 | 0 | 0 | 0 | 2 |
| FAgric | 1 | 0 | 2 | 0 | 0 | 3 |
| CED | 0 | 0 | 0 | 0 | 0 | 0 |

Table 08: Users

| Faculty | Students |  |  | Academic Staff | Admin Staff |
| --- | --- | --- | --- | --- | --- |
|  | Undergraduate | Masters | PhD |  |  |
| FEG | 630 | 26 | 0 | 47 | 16 |
| FEG Chimoio | 281 | 8 | 0 | 8 | 5 |
| FEG Tete | 0 | 0 | 0 | 10 | 3 |
| FMed | 400 | 16 | 0 | 26 | 23 |
| FGTI | 411 | 0 | 0 | 32 | 10 |
| FEC | 443 |  |  | 48 | 12 |
| FDir | 508 |  |  | 28 | 11 |
| FAgric | 309 | 0 | 0 | 21 | 6 |
| CED | 0 | 0 | 0 | 8 | 3 |

Annex 03: UCM campus distribution on the Mozambican Map

(Still to be inserted)